## Event Timeline
Core Responsibility Areas
| KEY TASK & MILESTONES | TIMELINE | POST EVENT | EVENT PLANNING | FINANCE | SPONSORSHIP | GRANT FUNDING | RISK MANAGEMENT/OPERATIONS | MARKETING PLAN | WORKING WITH MEDIA | DIGITAL MARKETING | VOLUNTEERS | LOGISTICS | EXECUTIVE AREA RESPONSIBLE | ✔
POST EVENT / PREPLANNING | Coordinate Thank you function and debrief | Post Festival - first week after | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 1
POST EVENT / PREPLANNING | Ensure any formal thank you and recognition required for all celebrities, volunteers and key stakeholders including sponsors , land owners, etc. is followed up with feedback encouraged | Post Festival - first week after | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 1
POST EVENT / PREPLANNING | Post event wrap up story and PR (newsletter, media, blog etc.) | Post Festival - first week after | ✔ | ✔ |  |  |  |  | ✔ | ✔ |  |  |  | MARKETING | 1
POST EVENT / PREPLANNING | PR - success of the festival! | Post Festival - first week after | ✔ | [5 empty] | ✔ | ✔ |  |  |  | MARKETING | 1
POST EVENT / PREPLANNING | Remove all signage and store in a central location for next year - update the asset register so you know what is there for next year! | Post Festival - first week after | ✔ | [9 empty] | ✔ | OPERATIONS | 1
POST EVENT / PREPLANNING | Hold a meeting with SES to discuss feedback on the traffic management, and provide recommendations to the committee for the following year | Post Festival - first week after | ✔ |  |  |  |  | ✔ | [5 empty] | OPERATIONS | 1
POST EVENT / PREPLANNING | Ensure all volunteers receive a formal letter of thanks – recognize them for the effort….include link to the feedback survey… | Post Festival - first week after | ✔ | [8 empty] | ✔ |  | VOLUNTEERS | 1
POST EVENT / PREPLANNING | Event report developed and presented to committee and stakeholders | Post Festival - second week after | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 2
POST EVENT / PREPLANNING | Check availability of site for next year + book | Post Festival - second week after | ✔ | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 2
POST EVENT / PREPLANNING | All sub committee coordinators to review their checklist and make adjustments ready to hand over to next years coordinator. | Post Festival - second week after | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 2
POST EVENT / PREPLANNING | Collate feedback data from surveys - Face to face and online | Post Festival - second week after | ✔ | ✔ |  |  |  |  | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 2
POST EVENT / PREPLANNING | Select date for next event and claim the date on Facebook and website | Post Festival - second week after | ✔ | ✔ | [9 empty] | EXECUTIVE COMMITTEE | 2
POST EVENT / PREPLANNING | Prepare and finalise all finances including wash up report | Post Festival - second week after | ✔ | ✔ | ✔ | [8 empty] | FINANCE | 2
POST EVENT / PREPLANNING | Post event finance wrap up report presented to committee | Post Festival - second week after | ✔ |  | ✔ | [8 empty] | FINANCE | 2
POST EVENT / PREPLANNING | Add a photo gallery to the website and send the link to the event coordinator for social media | Post Festival - second week after | ✔ | [5 empty] | ✔ |  | ✔ |  |  | MARKETING | 2
POST EVENT / PREPLANNING | Google analytics reports for debrief report | Post Festival - second week after | ✔ | [5 empty] | ✔ |  | ✔ |  |  | MARKETING | 2
POST EVENT / PREPLANNING | Post festival Event Manual - survey, next years claim the date, link to photo gallery, thank you to sponsors and visitors! | Post Festival - second week after | ✔ |  |  | ✔ |  |  | ✔ |  | ✔ |  |  | MARKETING | 2
POST EVENT / PREPLANNING | Funding acquittals | Post Festival - second week after | ✔ |  |  | ✔ |  |  | ✔ |  |  |  |  | MARKETING | 2
POST EVENT / PREPLANNING | Update Home page, News items etc. on the website | Post Festival - second week after | ✔ | [5 empty] | ✔ |  | ✔ |  |  | MARKETING | 2
PREPLANNING STAGE | Executive Committee Meeting - Strategy Session - SWOT Analysis, discuss goals & readdress vision, mission and values. Exec committee for next 12 months to be finalised. | 10 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 3
PREPLANNING STAGE | Review and update strategic plan, timeline and committee structure and determine changes/additions to be presented at public meeting | 10 months before festival |  | ✔ | [9 empty] | EXECUTIVE COMMITTEE | 3
PREPLANNING STAGE | Committee roles & responsibilities checklists updated ready to handover at the public meeting | 10 months before festival |  | ✔ | [7 empty] | ✔ |  | EXECUTIVE COMMITTEE | 3
PREPLANNING STAGE | Prepare packs to hand out to coordinators at public meeting - checklist, event manual, strategic plan, previous event report and recommendations | 10 months before festival |  | ✔ | [7 empty] | ✔ |  | EXECUTIVE COMMITTEE | 3
PREPLANNING STAGE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing! | Ongoing | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 3
PREPLANNING STAGE | Event budget developed and signed off by Executive | 10 months before festival |  | ✔ | ✔ | [8 empty] | FINANCE | 3
PREPLANNING STAGE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date | Ongoing |  |  | ✔ | [8 empty] | FINANCE | 3
PREPLANNING STAGE | Undertake review of website and implement changes and additions, ensuring it is in line with the festival theme and program | 10 months before festival |  | ✔ |  |  |  |  | ✔ |  | ✔ |  |  | MARKETING | 3
PREPLANNING STAGE | Marketing plan developed and signed off by Executive | 10 months before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 3
PREPLANNING STAGE | Coordinate meetings with major funding partners to lock away funding for the year | 10 months before festival |  |  |  |  | ✔ |  | ✔ |  |  |  |  | MARKETING | 3
PREPLANNING STAGE | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress | Ongoing |  |  |  | ✔ |  | ✔ | ✔ |  |  |  | ✔ | MARKETING | 3
PREPLANNING STAGE | Marketing and sponsorship acquisition and activation | Ongoing | [6 empty] | ✔ |  |  |  |  | MARKETING | 3
PREPLANNING STAGE | Gain quotes for all necessary infrastructure for the festival – this needs to be presented to the Executive for sign off prior to ordering. Once quotes are approved by Executive, place orders. | 10 months before festival | [5 empty] | ✔ |  |  |  |  | ✔ | OPERATIONS | 3
PREPLANNING STAGE | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required | Ongoing | [5 empty] | ✔ |  |  |  |  | ✔ | OPERATIONS | 3
PREPLANNING STAGE | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc. | Ongoing | [10 empty] | ✔ | OPERATIONS | 3
PREPLANNING STAGE | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers. | Ongoing |  | ✔ | [7 empty] | ✔ |  | VOLUNTEERS | 3
WORKING STAGE | Public meeting - allocate Sub Committee Coordinators to positions as per structure | 9 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 4
WORKING STAGE | Executive Committee Meeting | 9 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 4
WORKING STAGE | Develop the shell program and decide on feature elements, celebrities, entertainment etc. This then needs to be agreed at an executive level. | 9 months before festival |  | ✔ | [9 empty] | EXECUTIVE COMMITTEE | 4
WORKING STAGE | Lock in Live Music & Celebrities/Special Guests | 9 months before festival |  | ✔ | [9 empty] | EXECUTIVE COMMITTEE | 4
WORKING STAGE | Direct Mail to bus and coach groups + car clubs etc. (use left over programs from last festival to give them an idea of the program) | 9 months before festival | ✔ | ✔ |  |  |  |  | ✔ |  |  |  | ✔ | MARKETING | 4
WORKING STAGE | Website and social channels updated with date, celebrities, and other relevant content | 9 months before festival |  | ✔ |  |  |  |  | ✔ |  | ✔ |  |  | MARKETING | 4
WORKING STAGE | Develop sponsor prospectus and targeted hit list - start negotiations | 9 months before festival |  |  |  | ✔ |  |  | ✔ |  |  |  |  | MARKETING | 4
WORKING STAGE | Start working on Events traffic management plan + Events Management Plan (EMP). The EMP should include details of how traffic will be directed and how parking will be managed | 9 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 4
WORKING STAGE | Car Parks Plan - consider closely the movement of crowds and the flow of traffic. | 9 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 4
WORKING STAGE | Executive Committee Meeting | 8 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 5
WORKING STAGE | Review the post event report and action any items that have been recommended for improvement - pass on to sub committee coordinators as required | 8 months before festival |  | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 5
WORKING STAGE | Save the date collateral developed and distributed | 8 months before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 5
WORKING STAGE | Social media content plan developed and ready to commence next month | 8 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 5
WORKING STAGE | Electronic Direct Mail [EDM] monthly to commence | 8 months before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 5
WORKING STAGE | Continue sponsor negotiations, with the aim of locking away major sponsors this month - All sponsors who are also having a site space need to go through the same stallholder Expression Of Interest (EOI) process as everyone else (i.e. fill out Expression Of Interest (EOI) and include all necessary paperwork) | 8 months before festival |  |  |  | ✔ | ✔ |  | ✔ |  |  |  |  | MARKETING | 5
WORKING STAGE | Start developing travel packages for the event | 8 months before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 5
WORKING STAGE | Discuss Parcel Pick Up, Lost & Found, Requirements for number of toilets and location on site of the information tent. | 8 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 5
WORKING STAGE | Book SES for traffic management | 8 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 5
WORKING STAGE | Continue working on Events Traffic Management Plan + Events Management Plan - Involve police and emergency services in this process from early on. | 8 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 5
WORKING STAGE | Develop signage plan - directional and site signage | 8 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 5
WORKING STAGE | Book St Johns | 8 months before festival | [5 empty] | ✔ |  |  |  |  | ✔ | OPERATIONS | 5
WORKING STAGE | Finalise all quotes for infrastructure & Book | 8 months before festival | [5 empty] | ✔ |  |  |  |  | ✔ | OPERATIONS | 5
WORKING STAGE | Executive Committee Meeting | 7 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 6
WORKING STAGE | Address Risk Management Plan - does it need to be updated | 7 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | EXECUTIVE COMMITTEE | 6
WORKING STAGE | Ensure Bar Coordinator has RSA and licensing is in place | 7 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | EXECUTIVE COMMITTEE | 6
WORKING STAGE | Finalise all approvals, licenses, Insurance - Liquor License (Community Liquor Permit OLGR), traffic management, DA, APRA, Insurance renewed, road sign permits, food license, etc. | 7 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | EXECUTIVE COMMITTEE | 6
WORKING STAGE | Social media to start | 7 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 6
WORKING STAGE | Update all third party web listings with new details - ATDW, free event listings, etc. | 7 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 6
WORKING STAGE | Website updated with new content including sponsor details | 7 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 6
WORKING STAGE | Source advertising quotes and media partners | 7 months before festival | [6 empty] | ✔ | ✔ |  |  |  | MARKETING | 6
WORKING STAGE | Finalise sponsorship negotiations and ensure agreements are signed and filed | 7 months before festival |  |  |  | ✔ | ✔ |  | ✔ |  |  |  |  | MARKETING | 6
WORKING STAGE | Finalise travel packages and load to the website and ATDW | 7 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 6
WORKING STAGE | Finalise Events traffic management plan + Events Management plan and share with the committee so everyone is familiar - submit to council and local authorities | 7 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 6
WORKING STAGE | Contact emergency services re the event and supply with a copy of our Event Management Plan. Get them more involved before finalising this plan. | 7 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 6
WORKING STAGE | Executive Committee Meeting | 6 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 7
WORKING STAGE | Finalise Merchandise requirements for this years event & place any necessary orders | 6 months before festival |  | ✔ |  |  |  |  | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 7
WORKING STAGE | Finalise program shell ready to start approaching performers, stakeholders, etc. | 6 months before festival |  | ✔ |  |  |  |  | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 7
WORKING STAGE | Contact all sub committee coordinators and ask them to start sending details for the website | 6 months before festival |  | ✔ |  |  |  |  | ✔ |  |  | ✔ | ✔ | MARKETING | 7
WORKING STAGE | Load Expression Of Interest (EOI) documents [performers, stallholders, volunteers] to the website and put out a call on social media | 6 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 7
WORKING STAGE | Source all advertising quotes and media partner proposals | 6 months before festival | [6 empty] | ✔ | ✔ |  |  |  | MARKETING | 7
WORKING STAGE | Publicise local camping and accommodation options | 6 months before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 7
WORKING STAGE | Source local PR to announce the date and call for Performer Expression Of Interest (EOI) and Stallholder Expression Of Interest (EOI) | 6 months before festival | [6 empty] | ✔ | ✔ |  |  |  | MARKETING | 7
WORKING STAGE | Electronic Direct Marketing | 6 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 7
WORKING STAGE | Sponsorship contracts all signed and filed - time to put this to bed and start activation | 6 months before festival |  |  |  | ✔ |  |  | ✔ |  |  |  |  | MARKETING | 7
WORKING STAGE | Initial discussion and quote re sound and audio visual | 6 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 7
WORKING STAGE | Event Delivery Manual should be submitted to Council, Dept. of Main Roads and Local Police no later than this month. | 6 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 7
WORKING STAGE | Email all sub committee Coordinators requesting their list of required equipment for their section for event day. | 6 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 7
WORKING STAGE | Finalise all equipment requirements for event day and place orders. | 6 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 7
WORKING STAGE | Finalise the signage plan and determine the extra signage that requires production – send to designer or printer as required | 6 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 7
WORKING STAGE | Develop and finalise Volunteer Form using Survey Monkey | 6 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 7
WORKING STAGE | Executive Committee + Sub Committee Coordinators meeting | 5 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 8
WORKING STAGE | Develop more detailed program and schedules for event day. Gain feedback from sub committee coordinators and hand over to marketing coordinator | 5 months before festival |  | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 8
WORKING STAGE | Are all approvals, licenses and insurance matters locked away?! | 5 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | EXECUTIVE COMMITTEE | 8
WORKING STAGE | Lock in all advertising and promotion | 5 months before festival | [6 empty] | ✔ | ✔ | ✔ |  |  | MARKETING | 8
WORKING STAGE | Long lead media pitches | 5 months before festival | [6 empty] | ✔ | ✔ |  |  |  | MARKETING | 8
WORKING STAGE | Email, text or letter to mailing list database calling out for volunteers – mail runs, contact list, previous years volunteer list | 5 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 8
WORKING STAGE | Recruit NEW volunteers to assist the festival - mail runs, email list, school newsletters, community groups (think outside the box) | 5 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 8
WORKING STAGE | Advise the Volunteer Coordinator how many volunteers required based on structure | 4 months before festival |  | ✔ | [7 empty] | ✔ |  | EXECUTIVE COMMITTEE | 9
WORKING STAGE | All sub committee coordinators to notify volunteer coordinator of their volunteer needs and the finance coordinator of their float requirements. | 4 months before festival | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | FINANCE | 9
WORKING STAGE | Collateral designed, printed and distributed | 4 months before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 9
WORKING STAGE | Publicise local camping and accommodation options | 4 months before festival | [6 empty] | ✔ | ✔ |  |  |  | MARKETING | 9
WORKING STAGE | Web updates - program details, entertainment schedule and profiles, packages, sponsor details | 4 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 9
WORKING STAGE | Liaise with local council regarding town beatification and site preparation support | 4 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 9
WORKING STAGE | Commence site preparation - have a meeting with land owners to plan this | 4 months before festival | [10 empty] | ✔ | OPERATIONS | 9
WORKING STAGE | Distribute coordinator forms - liaise with all other coordinators to determine how many volunteers they need, when and if they have any particular requests for certain volunteers (prevents rostering those who are not needed) | 4 months before festival |  | ✔ | [7 empty] | ✔ |  | VOLUNTEERS | 9
WORKING STAGE | Executive Committee meeting | 3 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 10
WORKING STAGE | Finalise plans for opening ceremony welcome prior to festival. Organise caterers, invitations etc. and email. Decide on guest to open the event | 3 months before festival |  | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ |  |  | ✔ | EXECUTIVE COMMITTEE | 10
WORKING STAGE | Finalise the event site plan and share with all coordinators. Load to the website. | 3 months before festival |  | ✔ |  |  |  |  | ✔ |  |  |  | ✔ | EXECUTIVE COMMITTEE | 10
WORKING STAGE | Order all necessary food and supplies for the event - First Aid, Raffle tickets, water, etc. | 3 months before festival |  | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 10
WORKING STAGE | Finalise raffle and/or fundraising activities for the event | 3 months before festival |  | ✔ | ✔ | [8 empty] | EXECUTIVE COMMITTEE | 10
WORKING STAGE | Finalise Festival program and pass on to marketing coordinator | 3 months before festival |  | ✔ |  |  |  |  | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 10
WORKING STAGE | Program and schedules final and loaded to web, along with maps, bios, photos and as much content as possible | 3 months before festival |  | ✔ |  |  |  |  | ✔ |  | ✔ |  | ✔ | MARKETING | 10
WORKING STAGE | Advertising and promotion heavy from now on | 3 months before festival | [6 empty] | ✔ | ✔ | ✔ |  |  | MARKETING | 10
WORKING STAGE | Do a burst of Facebook advertising - focus on travel packages | 3 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 10
WORKING STAGE | Electronic Direct Marketing - announce event schedules, link to program, packages, social engagement for up to date details | 3 months before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 10
WORKING STAGE | Contact all sponsors and remind them to bring necessary promotional collateral and formally invite them to the event | 3 months before festival |  |  |  | ✔ | ✔ |  | ✔ |  |  |  |  | MARKETING | 10
WORKING STAGE | Remind SES about traffic management services for the event – manning of access roads and directions within parking lots. Hold another on-site meeting if required with local SES coordinator. | 3 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 10
WORKING STAGE | Work closely with Stallholder Coordinator to finalise facilities to support site plan placement including liaising with electrician regarding power requirements. Ensuring adequate equipment has been ordered and locked in. | 3 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 10
WORKING STAGE | Make arrangements for rubbish/waste management - consider recycling!!! | 3 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 10
WORKING STAGE | Continue sourcing volunteers | 3 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 10
WORKING STAGE | Go through all aspects of the event and confirm - performers, infrastructure, licensing etc. Set up a folder with everything for the day including contacts and necessary documents | 2 months before festival | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 11
WORKING STAGE | Executive Committee + Sub Committee Coordinators meeting | 2 months before festival |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 11
WORKING STAGE | Ensure all celebrities/performers are well briefed, logistics for transport and accommodation all arranged and locked in. | 2 months before festival |  | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 11
WORKING STAGE | Send a formal invitation to all key stakeholders, inviting them to the event. | 2 months before festival |  | ✔ |  | ✔ | ✔ | [6 empty] | EXECUTIVE COMMITTEE | 11
WORKING STAGE | Site preparation finalised and site plan shared with all stakeholders and volunteers | 2 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 11
WORKING STAGE | Plan seating and shade throughout the site and place orders. | 2 months before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 11
WORKING STAGE | On site meeting with Electrician, AV supplier and other key suppliers to ensure they are ready. | 2 months before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 11
WORKING STAGE | Arrange signage for different parking areas - stallholders, disabled, buses | 2 months before festival | [10 empty] | ✔ | OPERATIONS | 11
WORKING STAGE | Work with Volunteer Coordinator to ensure you have some volunteers to help you with signage starting next month | 2 months before festival | [9 empty] | ✔ | ✔ | OPERATIONS | 11
WORKING STAGE | Continue to source volunteers and continue drafting timetables/rosters | 2 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 11
WORKING STAGE | Ensure all volunteer forms are returned by the middle of this month. Roster must start to be finalised. | 2 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 11
WORKING STAGE | Plan Volunteer Thankyou function - send save the date ASAP. | 2 months before festival | [9 empty] | ✔ |  | VOLUNTEERS | 11
EVENT DELIVERY | Co-ordinators briefing – a formal briefing meeting so that all coordinators understand the complexity of the other coordinators roles – the aim is to ensure everyone is working together. | 1 month before festival | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Executive Committee + Sub Committee Coordinators meeting | 1 month before festival |  | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Finalise logistics including run sheets, rosters, MC notes, checklists, etc. | 1 month before festival |  | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Programs and site maps ready for hand out on the day + large copies for display at entrances and info tent | 1 month before festival |  | ✔ |  |  |  |  | ✔ |  |  |  | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Info tent planned and everything ready to set it up | 1 month before festival |  | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Review risk management plan and ensure all coordinators are thoroughly briefed | 1 month before festival |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | MC + Operations Co-ordinator to meet sound and vision people to finalise requirements | 1 month before festival |  | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Surveys developed and online - visitors, stallholders, sponsors | 1 month before festival | ✔ | ✔ |  |  |  |  | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Contact all Information and Troubleshooter volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival |  | ✔ | [7 empty] | ✔ |  | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Briefing with Volunteers, Committee, Stakeholder. Be sure to invite them to post festival thank you function | 1 month before festival |  | ✔ |  | ✔ | [5 empty] | ✔ |  | EXECUTIVE COMMITTEE | 12
EVENT DELIVERY | Liaise with the Executive Committee to finalise the announcer run sheets and notes including sponsor announcements | 1 month before festival |  | ✔ |  | ✔ |  |  | ✔ |  |  |  |  | MARKETING | 12
EVENT DELIVERY | Pre festival short lead PR | 1 month before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 12
EVENT DELIVERY | Electronic Direct Marketing - Checklist on what you need to prepare and what to bring | 1 month before festival | [6 empty] | ✔ |  |  |  |  | MARKETING | 12
EVENT DELIVERY | Short lead advertising to commence this month - TV and Radio | 1 month before festival | [6 empty] | ✔ | ✔ |  |  |  | MARKETING | 12
EVENT DELIVERY | Pre Event Electronic Direct Marketing - weather, maps/getting to the event, Instagram/hashtag, see you soon! | 1 month before festival | [6 empty] | ✔ |  | ✔ |  |  | MARKETING | 12
EVENT DELIVERY | Plan the communication method during the event [two ways] and make all necessary arrangements. | 1 month before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 12
EVENT DELIVERY | Buy necessary supplies and equipment for site signage erection | 1 month before festival |  | ✔ | [8 empty] | ✔ | OPERATIONS | 12
EVENT DELIVERY | Erect all direction signage as per the Signage Plan - with help of volunteers | 1 month before festival |  | ✔ | [7 empty] | ✔ | ✔ | OPERATIONS | 12
EVENT DELIVERY | Contact all your volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival. | 1 month before festival | [9 empty] | ✔ |  | VOLUNTEERS | 12
EVENT DELIVERY | Ensure all volunteer rosters finalised with enough volunteers schedule for set up and post event clean up | 1 month before festival | [9 empty] | ✔ |  | VOLUNTEERS | 12
EVENT DELIVERY | Finalise Survey's and get ready to post online | Festival - 2 weeks before | [6 empty] | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 13
EVENT DELIVERY | Send email to all Sub Committee Coordinators reminding them for float breakdown - pricing from all Stall Coordinators is required. Receive all float breakdown requests- chase up if required to ensure all ready to put floats together - keep in mind that pricing has a large effect on what is required in the float | Festival - 2 weeks before |  |  | ✔ | [8 empty] | FINANCE | 13
EVENT DELIVERY | Signs not to be erected until 1-2 weeks before festival and must be removed within 1 week post festival | Festival - 2 weeks before | [10 empty] | ✔ | OPERATIONS | 13
EVENT DELIVERY | Complete final rosters and send to each volunteer with induction pack (sign on/off, food handling guidelines, exact area they are working, etc.). | Festival - 2 weeks before | [9 empty] | ✔ |  | VOLUNTEERS | 13
EVENT DELIVERY | Develop MC notes | Festival - 1 week before |  | ✔ | [9 empty] | EXECUTIVE COMMITTEE | 14
EVENT DELIVERY | One week prior to the festival - Withdraw floats and set them up | Festival - 1 week before |  |  | ✔ | [8 empty] | FINANCE | 14
EVENT DELIVERY | Oversee all big infrastructure assembly | Festival - 1 week before | [10 empty] | ✔ | OPERATIONS | 14
EVENT DELIVERY | Send coordinators their final roster and contacts for their team, encouraging them to touch base (if they haven't done so already) ensure all team members are ready for the event. | Festival - 1 week before |  | ✔ | [7 empty] | ✔ |  | VOLUNTEERS | 14
EVENT DELIVERY | Monitor flow of visitors through site, queues etc. to make changes for next year | Festival Weekend | ✔ | ✔ | [8 empty] | ✔ | EXECUTIVE COMMITTEE | 15
EVENT DELIVERY | Walk around completing surveys | Festival Weekend | ✔ | ✔ |  |  |  |  | ✔ |  |  |  |  | EXECUTIVE COMMITTEE | 15
EVENT DELIVERY | Post LINK to Volunteer Form via Survey Monkey on website and promote via social media | Festival Weekend | ✔ | [5 empty] | ✔ |  | ✔ |  |  | MARKETING | 15
EVENT DELIVERY | Coordinate the set up and pull down of fencing and signage once the traffic management role has been completed. | Festival Weekend |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | OPERATIONS | 15
EVENT DELIVERY | Coordinate the bump in of all infrastructure on site | Festival Weekend |  | ✔ | [8 empty] | ✔ | OPERATIONS | 15
EVENT DELIVERY | Pre check with sound people well before the event start time | Festival Weekend |  | ✔ | [8 empty] | ✔ | OPERATIONS | 15
EVENT DELIVERY | Coordinate any communication between SES and MC during the day. Hold a debrief meeting with SES staff and Event volunteers once it is clear that the traffic management role has been completed on the day. | Festival Weekend |  | ✔ | [7 empty] | ✔ |  | OPERATIONS | 15
EVENT DELIVERY | Keep a close eye on traffic flow and re-direct cars into parks accordingly. | Festival Weekend |  | ✔ |  |  |  | ✔ | [5 empty] | OPERATIONS | 15
EVENT DELIVERY | Sound gear all set up | Festival Weekend | [10 empty] | ✔ | OPERATIONS | 15
EVENT DELIVERY | Erect all site signage | Festival Weekend | [10 empty] | ✔ | OPERATIONS | 15
EVENT DELIVERY | Monitor signage to ensure it has not been removed or wind damaged | Festival Weekend | [5 empty] | ✔ |  |  |  |  | ✔ | OPERATIONS | 15
EVENT DELIVERY | Reallocate volunteers to areas if necessary - ensuring everyone has adequate support | Festival Weekend | [9 empty] | ✔ |  | VOLUNTEERS | 15
EVENT DELIVERY | Hand over name tags/lanyards for volunteers and farmers as they arrive | Festival Weekend | [9 empty] | ✔ |  | VOLUNTEERS | 15
EVENT DELIVERY | Coordinate floaters and roamers and be a support person during the day…. | Festival Weekend |  |  | ✔ | [8 empty] | VOLUNTEERS | 15
EVENT DELIVERY | Ensure stalls/coordinators have enough helpers | Festival Weekend | [9 empty] | ✔ |  | VOLUNTEERS | 15
EVENT DELIVERY | Coordinate Volunteer roster at information tent | Festival Weekend | [9 empty] | ✔ |  | VOLUNTEERS | 15