## Post Event Briefing
Meeting Agenda
Your Festival / Event Name
Meeting Title | Post Event Briefing - 2-4 weeks after the event / festival
Date
Time
Location
Attendees Reqd: | Members of Executive Committee /Sub Committee / Stakeholders
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Coordinate Thank you function and debrief
EXECUTIVE COMMITTEE | Ensure any formal thank you and recognition required for all celebrities, volunteers and key stakeholders inc. sponsors , land owners, etc is followed up with feedback encouraged
MARKETING | Post event wrap up story and PR (newsletter, media, blog etc)
MARKETING | PR - success of the festival!
OPERATIONS | Hold a meeting with SES to discuss feedback on the traffic management, and provide recommendations to the committee for the following year
OPERATIONS | Remove all signage and store in a central location for next year - update the asset register so you know what is there for next year!
VOLUNTEERS | Ensure all volunteers receive a formal letter of thanks – recognize them for the effort….include link to the feedback survey…
EXECUTIVE COMMITTEE | Event report developed and presented to committee and stakeholders
FINANCE | Post event finance wrap up report presented to committee
EXECUTIVE COMMITTEE | Check availability of site for next year + book
EXECUTIVE COMMITTEE | Collate feedback data from surveys - Face to face and online
EXECUTIVE COMMITTEE | All sub committee coordinators to review their checklist and make adjustments ready to hand over to next years cooridnator.
EXECUTIVE COMMITTEE | Select date for next event and claim the date on Facebook and website
FINANCE | Prepare and finalise all finances including wash up report
MARKETING | Add a photo gallery to the website and send the link to the event coordinator for social media
MARKETING | Google analytics reports for debrief report
MARKETING | Post festival EDM - survey, next years claim the date, link to photo gallery, thank you to sponsors and visitors!
MARKETING | Funding acquittals
MARKETING | Update Home page, News items etc on the website
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 11 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 11 Months to Go - Event Festival Strategy Session
Date
Time
Location
Attendees Reqd: | Members of Executive Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· Strategy - review goals, vision & mission and update as necessary
· Executive Committee appointed for festival
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Executive Committee Meeting - Strategy Session - SWOT Analysis, discuss goals & readdress vision, mission and values. Exec committee for next 12 months to be finalised.
EXECUTIVE COMMITTEE | Review and update strategic plan, timeline and committee structure and determine changes/additions to be presented at public meeting
EXECUTIVE COMMITTEE | Committee roles & responsibilities checklists updated ready to handover at the public meeting
EXECUTIVE COMMITTEE | Prepare packs to hand out to coordinators at next months public meeting - checklist, event manual, strategic plan, previous event report and recommendations
FINANCE | Event budget developed and signed off by Executive
MARKETING | Undertake review of website and implement changes and additions, ensuring it is in line with the festival theme and program
MARKETING | Marketing plan developed and signed off by Executive
MARKETING | Coordinate meetings with major funding partners to lock away funding for the year
OPERATIONS | Gain quotes for all necessary infrastructure for the festival – this needs to be presented to the Executive for sign off prior to ordering. Once quotes are approved by Executive, place orders.
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 10 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 10 Months to Go - The Public Meeting followed by Executive Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee / General Public / Sub Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· Sub Committee Coordinators appointed
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Public meeting - allocate Sub Committee Coordinators to positions as per structure
EXECUTIVE COMMITTEE | Hand out Committee roles & responsibilities checklists
EXECUTIVE COMMITTEE | Handout Information Packs - checklist, event manual, strategic plan, previous event report and recommendations
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 9 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 9 Months to Go - Executive & Coordinators Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee / Sub Committee Team
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Develop the shell program and decide on feature elements, celebrities, entertainment etc. This then needs to be agreed at an executive level.
EXECUTIVE COMMITTEE | Lock in Live Music & Celebrities/Special Guests
MARKETING | Direct Mail to bus and coach groups + car clubs etc. (use left over programs from last festival to give them an idea of the program)
MARKETING | Website and social channels updated with date, celebrities, and other relevant content
MARKETING | Develop sponsor prospectus and targeted hit list - start negotiations
OPERATIONS | Start working on Events traffic management plan + Events Management Plan (EMP). The EMP should include details of how traffic will be directed and how parking will be managed
OPERATIONS | Car Parks Plan - consider closely the movement of crowds and the flow of traffic.
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 8 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 8 Months to Go - Executive Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
MARKETING | Save the date collateral developed and distributed
MARKETING | Social media content plan developed and ready to commence next month
MARKETING | Electronic Direct Mail [EDM] monthly to commence
MARKETING | Continue sponsor negotiations, with the aim of locking away major sponsors this month - All sponsors who are also having a site space need to go through the same stallholder Expression Of Interest (EOI) process as everyone else (i.e. fill out Expression Of Interest (EOI) and include all necessary paperwork)
MARKETING | Start developing travel packages for the event
OPERATIONS | Discuss Parcel Pick Up, Lost & Found, Requirements for number of toilets and location on site of the information tent.
OPERATIONS | Book SES for traffic management
OPERATIONS | Continue working on Events Traffic Management Plan + Events Management Plan - Involve police and emergency services in this process from early on.
OPERATIONS | Develop signage plan - directional and site signage
OPERATIONS | Book St Johns
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 7 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 7 Months to Go - Executive Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Address Risk Management Plan - does it need to be updated
EXECUTIVE COMMITTEE | Ensure Bar Coordinator has RSA and licensing is in place
EXECUTIVE COMMITTEE | Finalise all approvals, licenses, Insurance - Liquor License (Community Liquor Permit OLGR), traffic management, DA, APRA, Insurance renewed, road sign permits, food license, etc.
MARKETING | Social media to start
MARKETING | Update all third party web listings with new details - ATDW, free event listings, etc.
MARKETING | Website updated with new content including sponsor details
MARKETING | Source advertising quotes and media partners
MARKETING | Finalise sponsorship negotiations and ensure agreements are signed and filed
MARKETING | Finalise travel packages and load to the website and ATDW
OPERATIONS | Finalise Events traffic management plan + Events Management plan and share with the committee so everyone is familiar - submit to council and local authorities
OPERATIONS | Contact emergency services re the event and supply with a copy of our Event Management Plan. Get them more involved before finalising this plan.
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 6 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 6 Months to Go - Executive and Coordinators Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee / Sub Committee Team
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Finalise Merchandise requirements for this years event & place any necessary orders
EXECUTIVE COMMITTEE | Finalise program shell ready to start approaching performers, stakeholders, etc.
MARKETING | Contact all sub committee coordinators and ask them to start sending details for the website
MARKETING | Load Expression Of Interest (EOI) documents [performers, stallholders, volunteers] to the website and put out a call on social media
MARKETING | Source all advertising quotes and media partner proposals
MARKETING | Publicise local camping and accommodation options
MARKETING | Source local PR to announce the date and call for Performer Expression Of Interest (EOI) and Stallholder Expression Of Interest (EOI)
MARKETING | Electronic Direct Marketing
MARKETING | Sponsorship contracts all signed and filed - time to put this to bed and start activation
OPERATIONS | Initial discussion and quote re sound and audio visual
OPERATIONS | Event Delivery Manual should be submitted to Council, Dept. of Main Roads and Local Police no later than this month.
OPERATIONS | Email all sub committee Coordinators requesting their list of required equipment for their section for event day.
OPERATIONS | Finalise all equipment requirements for event day and place orders.
OPERATIONS | Finalise the signage plan and determine the extra signage that requires production – send to designer or printer as required
VOLUNTEERS | Develop and finalise Volunteer Form using Survey Monkey
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 5 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 5 Months to Go - Executive Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Develop more detailed program and schedules for event day. Gain feedback from sub committee coordinators and hand over to marketing coordinator
EXECUTIVE COMMITTEE | Are all approvals, licenses and insurance matters locked away?
MARKETING | Lock in all advertising and promotion
MARKETING | Long lead media pitches
VOLUNTEERS | Email, text or letter to mailing list database calling out for volunteers – mail runs, contact list, previous years volunteer list
VOLUNTEERS | Recruit NEW volunteers to assist the festival - mail runs, email list, school newsletters, community groups (think outside the box)
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 4 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 4 Months to Go - Executive Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Advise the Volunteer Coordinator how many volunteers required based on structure
FINANCE | All sub committee coordinators to notify volunteer coordinator of their volunteer needs and the finance coordinator of their float requirements.
MARKETING | Collateral designed, printed and distributed
MARKETING | Publicise local camping and accommodation options
MARKETING | Web updates - program details, entertainment schedule and profiles, packages, sponsor details
OPERATIONS | Liaise with local council regarding town beatification and site preparation support
OPERATIONS | Commence site preparation - have a meeting with land owners to plan this
VOLUNTEERS | Distribute coordinator forms - liaise with all other coordinators to determine how many volunteers they need, when and if they have any particular requests for certain volunteers (prevents rostering those who are not needed)
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 3 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 3 Months to Go - Executive and Coordinators Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee / Subcommittee Team
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Finalise plans for opening ceremony welcome prior to festival. Organise caterers, invitations etc. and email. Decide on guest to open the event
EXECUTIVE COMMITTEE | Finalise the event site plan and share with all coordinators. Load to the website.
EXECUTIVE COMMITTEE | Order all necessary food and supplies for the event - First Aid, Raffle tickets, water, etc.
EXECUTIVE COMMITTEE | Finalise raffle and/or fundraising activities for the event
EXECUTIVE COMMITTEE | Finalise Festival program and pass on to marketing coordinator
MARKETING | Program and schedules final and loaded to web, along with maps, bios, photos and as much content as possible
MARKETING | Advertising and promotion heavy from now on
MARKETING | Do a burst of Facebook advertising - focus on travel packages
MARKETING | Electronic Direct Marketing - announce event schedules, link to program, packages, social engagement for up to date details
MARKETING | Contact all sponsors and remind them to bring necessary promotional collateral and formally invite them to the event
OPERATIONS | Remind SES about traffic management services for the event – manning of access roads and directions within parking lots. Hold another on-site meeting if required with local SES coordinator.
OPERATIONS | Work closely with Stallholder Coordinator to finalise facilities to support site plan placement including liaising with electrician regarding power requirements. Ensuring adequate equipment has been ordered and locked in.
OPERATIONS | Make arrangements for rubbish/waste management - consider recycling!!!
VOLUNTEERS | Continue sourcing volunteers
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 2 Months to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 2 Months to Go - Executive and Coordinator Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee / Subcommittee Team
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Schedule date this month for Pre Event Coordinator and Stakeholder Debrief Meeting
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Continually review the post event report from the previous year to ensure the enhancements and changes are taken into consideration. In addition always watch out for trends and what other events are doing!
FINANCE | Manage the set event budget - issue and pay invoices and keep budget forecast/actuals budget up to date
MARKETING | Send regular updates to all sponsors, partners and stakeholders to keep them informed of festival planning progress
MARKETING | Marketing and sponsorship acquisition and activation
OPERATIONS | Regular communication with infrastructure providers to develop a good working relationship and keep abreast of new requirements as required
OPERATIONS | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents/tables/chairs/cash drawers etc.
VOLUNTEERS | Maintain the volunteer roster; liaise with sub committee Coordinators to look at the gaps and consider how to fill them. Regularly recruit new volunteers.
EXECUTIVE COMMITTEE | Go through all aspects of the event and confirm - performers, infrastructure, licensing etc. Set up a folder with everything for the day including contacts and necessary documents
EXECUTIVE COMMITTEE | Ensure all celebrities/performers are well briefed, logistics for transport and accommodation all arranged and locked in.
EXECUTIVE COMMITTEE | Send a formal invitation to all key stakeholders, inviting them to the event.
OPERATIONS | Site preparation finalised and site plan shared with all stakeholders and volunteers
OPERATIONS | Plan seating and shade throughout the site and place orders.
OPERATIONS | On site meeting with Electrician, AV supplier and other key suppliers to ensure they are ready.
OPERATIONS | Arrange signage for different parking areas - stallholders, disabled, buses
OPERATIONS | Work with Volunteer Coordinator to ensure you have some volunteers to help you with signage starting next month
VOLUNTEERS | Continue to source volunteers and continue drafting timetables/rosters
VOLUNTEERS | Ensure all volunteer forms are returned by the middle of this month. Roster must start to be finalised.
VOLUNTEERS | Plan Volunteer Thankyou function - send save the date ASAP.
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## 1 Month to Go
Meeting Agenda
Your Festival / Event Name
Meeting Title | 1 Month to Go - Executive Meeting
Date
Time
Location
Attendees Reqd: | Members of Executive Committee
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do this month…
EXECUTIVE COMMITTEE | Plan the Co-ordinators briefing – a formal briefing meeting so that all coordinators understand the complexity of the other coordinators roles – the aim is to ensure everyone is working together.
EXECUTIVE COMMITTEE | Finalise logistics including run sheets, rosters, MC notes, checklists, etc.
EXECUTIVE COMMITTEE | Programs and site maps ready for hand out on the day + large copies for display at entrances and info tent
EXECUTIVE COMMITTEE | Info tent planned and everything ready to set it up
EXECUTIVE COMMITTEE | Review risk management plan and ensure all coordinators are thoroughly briefed
EXECUTIVE COMMITTEE | MC + Operations Co-ordinator to meet sound and vision people to finalise requirements
EXECUTIVE COMMITTEE | Surveys developed and online - visitors, stallholders, sponsors
EXECUTIVE COMMITTEE | Contact all Information and Troubleshooter volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival.
EXECUTIVE COMMITTEE | Briefing with Volunteers, Committee, Stakeholder. Be sure to invite them to post festival thank you function
MARKETING | Liaise with the Executive Committee to finalise the announcer run sheets and notes including sponsor announcements
MARKETING | Pre festival short lead PR
MARKETING | Electronic Direct Marketing - Checklist on what you need to prepare and what to bring
MARKETING | Short lead advertising to commence this month - TV and Radio
MARKETING | Pre Event Electronic Direct Marketing - weather, maps/getting to the event, Instagram/hashtag, see you soon!
OPERATIONS | Plan the communication method during the event [two ways] and make all necessary arrangements.
OPERATIONS | Buy necessary supplies and equipment for site signage erection
OPERATIONS | Erect all direction signage as per the Signage Plan - with help of volunteers
VOLUNTEERS | Contact all your volunteers prior to the event and ensure they are aware of requirements, timing and are prepared for their shift (volunteer coordinator to provide contacts). Ensure they are invited to the volunteer thank you function at the end of the festival.
VOLUNTEERS | Ensure all volunteer rosters finalised with enough volunteers schedule for set up and post event clean up
EXECUTIVE COMMITTEE | Finalise Survey's and get ready to post online
FINANCE | Send email to all Sub Committee Coordinators reminding them for float breakdown - pricing from all Stall Coordinators is required. Receive all float breakdown requests- chase up if required to ensure all ready to put floats together - keep in mind that pricing has a large effect on what is required in the float
OPERATIONS | Signs not to be erected until 1-2 weeks before festival and must be removed within 1 week post festival
VOLUNTEERS | Complete final rosters and send to each volunteer with induction pack (sign on/off, food handling guidelines, exact area they are working, etc.).
EXECUTIVE COMMITTEE | Develop MC notes
FINANCE | One week prior to the festival - Withdraw floats and set them up
OPERATIONS | Oversee all big infrastructure assembly
VOLUNTEERS | Send coordinators their final roster and contacts for their team, encouraging them to touch base (if they haven't done so already) ensure all team members are ready for the event.
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close

## PreEvent Briefing
Meeting Agenda
Your Festival / Event Name
Meeting Title | Pre-Event Briefing - 1 - 2 weeks before
Date
Time
Location
Attendees Reqd: | Members of Executive Committee / Subcommittee / Volunteers / Stakeholders
*TIP: The Event Coordinator / Secretary should take both the Meeting Minutes and the Meeting Agenda to each relevant meeting – making sure that the meeting agenda is emailed out before hand.
Meeting Overview
Event Coordinator / Secretary | · Apologies
· Correspondence coming in
· Business arising from Minutes of previous meeting
· Committee's report – current overview of event planning
· General Event Planning Checklist
· Financials
General Event Planning Checklist – Things to do a few days before and on the day of the event
EXECUTIVE COMMITTEE | Discuss how to monitor flow of visitors through site, queues etc. to make changes for next year
EXECUTIVE COMMITTEE | Walk around during the event completing surveys - who is doing this?
MARKETING | Post LINK to Volunteer Form via Survey Monkey on website and promote via social media
OPERATIONS | Coordinate the set up and pull down of fencing and signage once the traffic management role has been completed.
OPERATIONS | Coordinate the bump in of all infrastructure on site
OPERATIONS | Pre check with sound people well before the event start time
OPERATIONS | Coordinate any communication between SES and MC during the day. Hold a debrief meeting with SES staff and Event volunteers once it is clear that the traffic management role has been completed on the day.
OPERATIONS | Keep a close eye on traffic flow and re-direct cars into parks accordingly.
OPERATIONS | Sound gear all set up
OPERATIONS | Erect all site signage
OPERATIONS | Monitor signage to ensure it has not been removed or wind damaged
VOLUNTEERS | Reallocate volunteers to areas if necessary - ensuring everyone has adequate support
VOLUNTEERS | Hand over name tags/lanyards for volunteers and farmers as they arrive
VOLUNTEERS | Coordinate floaters and roamers and be a support person during the day….
VOLUNTEERS | Ensure stalls/coordinators have enough helpers
VOLUNTEERS | Coordinate Volunteer roster at information tent
Financials Update
Finance Coordinator | · Consideration of previous meetings financial matters
· Summary of Current Financial statements
· Budget Overview
Meeting Close